## Sheet1
Sprint Items: | Size: | Points: | Sprint 1 | Sprint 2 | Sprint 3 | Key:
Re-learn Basic HTML | L | 8 | 8 |  |  | 27.3333 points Per Sprint
Set up basic homepage | S | 4 | 4
Supply information for homepage | S | 4 |  | 4
Create database system with all the restone items | XL | 16 | 16
Create a way to link separate pages to the items in the data base | L | 8 |  | 8
Simple Redstone Explanation pages done | L | 8 |  |  | 8
Harder Redstone Explanation pages done | XL | 16 |  | 16
Expert Redstone Explanantions pages done | XL | 16 |  |  | 16
Test Information validity | XS | 2 |  |  | 2
|  | 82 | 28 | 28 | 26